## Sheet1
Requirment Name | Effects | Time cost | Executable | Backend Time | Frontend time | FrontEnd Iman | BackEnd Mohamad | Note
Prototype for all interfaces | delay on the development step | High | Yes | 300 |  |  |  | It was sample for user interfaces then become prototype
Dynamic dashboard |  | High | Yes |  |  | 5
Library and Installation
Validation and Condition | UI, ERD and Logic | Medium | Yes | 7 | 6 | 6
Add dynamic attributes by type not only by row | UI and Logic | High | Yes | 3 | 3 | 5
Dependency | UI, ERD and Logic | High | Yes | 6 | 6 | 6 |  | Effects the project performance
Dependency related to all layers of entites not only the specific table | UI, ERD and Logic | High | Yes | 10 | 5 | 8
Edit and disable dynamic attributes | UI, ERD and Logic | High | Yes | 4 | 2 | 2 |  | It will be disable (soft delete) instead of delete
Edit and disable static attributes | UI, ERD and Logic | High | Yes | 10 | 8 | 2 |  | It will be disable (soft delete) instead of delete
History for attributes | UI, ERD and Logic | Medium | Yes | 4 | 2 | 20
|  |  |  | 44 | 32 | 49
Workflow and Integration
Paralle steps | UI, ERD and Logic | High | Yes | 6 | 4 | 10
Reminder action | UI, ERD and Logic | Medium | Yes | 3 | 2 | 5
Esclation action | UI, ERD and Logic | Medium | Yes | 8 | 6 | 3
Apply mail stracture with variables | UI, ERD and Logic | High | Yes | 5 | 3 | 5
Add actor to groups | UI, ERD and Logic | Medium | Yes | 4 | 3 | 3
Configration for agreed APIs | UI, ERD and Logic | High | Yes | 5 | 4 | 10
Integration action | UI, ERD and Logic | High | Yes | 11 | 7 | 10
Integration list action(get and save it in list then post) | UI, ERD and Logic | High | Yes | 11 | 8 | 10
Deal with autentication system and check token | UI, ERD and Logic | Medium | Yes | 8 | 6 | 6
|  |  |  | 61 | 43 | 62
Report
Dynamic Report | UI, ERD and Logic | High | Yes |  |  | 15
Dynamic Dashboard | UI, ERD and Logic | High | Yes | 13 | 10 | 15
Dashboard Filters & Order | UI, ERD and Logic | High | Yes | 10 | 7 | 10
|  |  |  | 23 | 17 | 25
Free Featuters Offered by ICI
Data type for dynamic attributes | UI, ERD and Logic |  | Yes | 2 | 1 | 2
Adding filter for all models and view | UI |  | Yes | 6 | 3 | 5
Edit civil validation action in workflow | UI, ERD and Logic |  | Yes | 3 | 1 | 2
More flexibilty in user and role management | UI, ERD and Logic |  | Yes | 4 | 2 | 10
Applying workflow on multi sites, areas or regions | UI and Logic |  | Yes | 2 | 1 | 2
Adding description for attributes | UI, ERD and Logic |  | Yes | 2 | 2 | 2
Adding external groups | UI, ERD and Logic |  | Yes | 2 | 1 | 1
Adding Filter in attributes management interface | UI and Logic |  | Yes | 2 | 2 | 2
|  |  |  | 23 | 13 | 26
New Requirments After CR3
Time for mapping attrbuites between dummy data and data structure | Time | Medium |  | 6 |  |  |  | It is related to data migration, it will be finished after we receive the approval and confirmation for data mapping
Adding new attributes to the database (so the related code will be modified) | UI, ERD and API | Medium |  | 4 | 3 | 3
Clean the data and unify units for all attributes | Time, ERD and Logic | Medium |  | 4
Add new rules and validations | UI, ERD and Logic | Medium |  | depends if there is new rules or not |  |  |  | We asked Syriatel team to provide us with the rules that are not existed in toad
Change the view (display attributes related to the library in installation interface) | UI and Logic | High |  | 5 | 4 | 4
Dynamic tables with filters in all interfaces (library and installation) | UI, ERD and Logic | High |  | 13 | 10 | 10 |  | We have to change part of the code in order to apply this feature Tables will contain fields related to more than one table (library, installation and dynamic attributes)
|  |  |  | 26 | 23 | 17
Requirements related to map
Save history and filters | UI, ERD and Logic |  | Yes | 5 | 6 |  |  | user will be able to merge between filters but not between history
Query builder |  |  | it's a huge requirment and we propose another solution to achieve the request in the note section | 7 | 9 |  |  | user will be able to create multible filters and the relation between filters will be "or" .Inside one layer the relation will be "and" . If user need "or" relation inside the same layer he has to create two filters P.S The estimated time is for this solution
Switching between map and inventory with filters |  |  |  | 6 | 7 |  |  | Syriatel team requested this point in the previous meetings "without filters"
Dynamic layers and filters (all attributes are subject to be filter) |  |  |  | 8 | 5
|  |  |  | 26 | 27
|  | Grand Total of above |  | 203 | 155 | 184
|  | Analysis 2 |  | 92
Prototype 2
|  | Grand Total |  | 295 | 155 | 184