## Sheet1
Requirment Name | Effects | Time cost | Execute | Backend Time | Frontend time | BackEnd Mohamad | FronEnd Iman | Note
It was sample for user interfaces then become prototype for all interfaces | delay development step | High cost | yes | 300
Dynamic dashboard |  | hight cost | yes
Library and Installation
Validation and Condition | UI , ERD and logic | Medium cost | yes | 7 | 6
Add Dynamic attributes by type not only by row | UI ,logic |  | yes | 3 | 3
Dependency | UI , ERD and logic | High cost and effect to project performance | yes | 6 | 6
Dependency related to all layer of entites not only the specific table |  | Hight cost | yes | 10 | 5
Edit and Delete for dynamic att | UI , ERD and logic | Medium cost | yes | 4 | 2 |  |  | It will be disable att
Edit and Delete for static att | UI , ERD and logic | High cost | yes | 10 | 8 |  |  | It will be disable att
History for att |  | Medium cost | yes | 4 | 2
|  |  |  | 44 | 32
Workflow and integration
Paralle steps | UI , ERD and logic |  | yes | 6 | 4
Reminder action | UI , ERD and logic |  | yes | 3 | 2
Esclation action | UI , ERD and logic |  | yes | 8 | 6
Apply mail stracture with variables | UI , ERD and logic |  | yes | 5 | 3
Add actor to groups | UI , ERD and logic |  | yes | 4 | 3
Configration for agreed APIs | UI , ERD and logic |  | yes | 5 | 4
Integration action | UI , ERD and logic |  | yes | 11 | 7
Integration list action(get and save it in list then post) | UI , ERD and logic |  | yes | 11 | 8
Deal with autentication system and check token | UI , ERD and logic |  | yes | 8 | 6
|  |  |  | 61 | 43
Report
Dynamic charts | UI , ERD and logic |  | yes | 13 | 10
Filter in charts | UI , ERD and logic |  | yes | 10 | 7
|  |  |  | 23 | 17
without adding cost
Data type for dynamic attributes | UI , ERD and logic |  | yes | 2 | 1
Adding filter for all models and view | UI |  | yes | 6 | 3
Edit civil validation action in workflow | UI , ERD and logic |  | yes | 3 | 1
More flexibilty in user and role management | UI , ERD and logic |  | yes | 4 | 2
Apply workflow by site or region | UI ,logic |  | yes | 2 | 1
Description for att | UI , ERD and logic |  | yes | 2 | 2
Adding external group | UI , ERD and logic |  | yes | 2 | 1
Filter for manage att | UI,logic |  | yes | 2 | 2
|  |  |  | 23 | 13
Requirments after CR3
time for mapping attrbuites between dummy data and data structure | time |  |  | 6 |  |  |  | it is related to data migration, it will be finish after we receive the approval and confirmation for data mapping
Adding new attributes to the database (so that part of the code will be modified) | UI,API and ERD |  |  | 4 | 3
clean the data and unify units for all attributes | time ,ERD and logic |  |  | 4
add new rules and validation | UI,ERD and logic |  |  | depends if there is new rules or not |  |  |  | we ask syriatel to provide us with the rules that are not existed in toad
change the view (display attributes related to the library in installation interface) | UI and Logic |  |  | 5 | 4
dynamic tables with filters in all interfaces (library and installation) |  |  |  | 13 | 8 |  |  | we have to change part of the code after this feature tables will contains filled related to more than one table (library ,installation and dynamic attributes)
|  |  |  | 26 | 21
Requirements related to map
save history and filters | ERD,UI and logic |  | yes | 5 | 6 |  |  | user will be able to merge between filters but not between history
query builder |  |  | it's a huge requirment and we propose another solution to achieve the request in the note section | 7 | 9 |  |  | user will be able to create multible filters and the relation between filters will be "or" .Inside one layer the relation will be "and" . If user need "or" relation inside the same layer he has to create two filters P.S The estimated time is for this solution
switching between map and inventory with filters |  |  |  | 6 | 7 |  |  | Syriatel team requested this point in the previous meetings "without filters"
dynamic layers and filters (all attributes are subject to be filter) |  |  |  | 8 | 5
|  |  |  | 26 | 27
|  | Grand Total of above |  | 203 | 153
|  | Analysis 2 |  | 92
Prototype 2
|  | Grand total |  | 295 | 153